## Scope
Software Installation |  | Software installation and code run on system
Admin portal | Shyam | Home page | 1. Log in with different user in admin portal 2. Forgot password feature 3. Change language option | Partially Done | Done Login. Forget password- [Note: Email service automation framework limitation] | 15 Days (3 Weeks)
|  | User Page | 1.User creation/update/deletion 2.Email id check (uniqueness of id) / Email send to user email id | Done
| Shyam | Organisation Page | 1. Organisation & Sub-Organisation creation/update/deletion 2. Scheduler policy | Pending | Due to Super User credential has one time work. Need to make test plan accordingly.
| Ankit | Service user Page | Service user page 1. Create/Delete User prefrences form 2. Create/Delete User blacklist form 3. Create/Delete message user form 4. Create/Delete Survey form for questionaire 5. Create/Delete template form for organisationwise questionaire | Done
|  | Carer page | Carer page 1. Create/Delete carer availability form 2. Create/Delete leave/activity plan form 3. Create/Delete carer skills form 4. Create/Delete carer preferences 5. Create/Delete unrecorded visits 6. Create/delete message for carer form | Done
| Shyam | Carer Package Page | Carer package page 1. Create/Delete task planning for carer 2. Create/Delete package type for invoice calculation 3. Create/Delete assigning routines to service user | Done
| Shyam | Scheduler Page | Schedule saving and publish for Service user and carer | Pending | 1. Issue on Scheduler page. 2. Need to make test plan accordingly because this page integrate with multiple pages and plateform.
| Shyam | Dashboard Page | Dashboard graphs creation | Pending | Need discussion with vivek ji, how to automate dashboard because it shows only graphs.
|  | Reports Page | Reports creation | Pending | Need discussion with vivek ji, how to automate reports
|  | Permission mapping Page | Automatic mapping | Pending | Need to work on that
Support Portal |  | Home page | 1. Log in with different user in support portal 2. Forgot password feature | Pending | Not started working on support portal yet.
|  | OEM | OEM definition for Installations | Pending | Not started working on support portal yet. | 20 Days (4 Weeks)
| Sachin | Assets | Assets import for set up and generating reports | Pending | Not started working on support portal yet.
| Sachin | OTA | 1.Create firmware repository 2. Automatic OTA file/OTA file template export 3. Request fire for firmware upgrade/rollback/abort 4. Report generation for OTA | Pending | Not started working on support portal yet.
| Sachin | Reports | Export OEM Gateway detailed report | Pending | Not started working on support portal yet.
| Sachin | Diagnostics | 1. Send command to gateway for SSH service and log copy of gatway and tablet app 2. Report generation | Pending | Not started working on support portal yet.
|  | Admin | 1. Create/Delete user definition form for users (Call centre, technical person etc) 2. Create/Delete user group and mapping with organisation | Pending | Not started working on support portal yet.
|  | Change password | Create/Delete profile and change password | Pending | Not started working on support portal yet.
|  | Support | 1. Switching page for alert screen, all alerts for different installations alert 2. Excecute query tool 3. Send request to access tablet app on remote | Pending | Not started working on support portal yet.
| Sachin | Log out | Log out from support portal automatically | Pending | Not started working on support portal yet.
Cared For Application |  | Home screen | 1.Change temperature 2. Switch mode (Day/Night) 3. SOS Cycle 5. Feedback after carer visit 5.Clock IN/OUT feature for carer 6. Check Profile,App info page 7. Send logs option | Partially Done | Cover SOS part with regression cycle. Pending other feature. | 10 Days (2 Weeks)
|  | App upgrade | Automatic app upgrade | Pending | Need to discuss how to implement apart from regression cycle
|  |  | Picture change | Pending | Need to discuss how to implement apart from regression cycle
|  | Reconfigure Wi-Fi | Automatic switch between Wi-Fi using reconfigure Wi-Fi feature | Pending | Need to discuss how to implement apart from regression cycle
Carer Application |  | Responder | 1. Emergency/Non-Emergency alerts flow 2. Check schedule visit of carer and also details of task 3. Change temperature and mode of day/night 4. Check user status of service user, carer visit details, and sleep quality 5. Set schedule for heating, sleep schedule, Away settings, feedback 6.Send app logs | Partially Done | Cover alert part with regression cycle. Pending other feature. | 20 Days (4 Weeks)
|  | carer | 1.Visit reminder messaged 2. Schedules | Pending | Need to discuss how to implement apart from regression cycle
|  | Log out | Auto log from apps | Pending | Need discussion with vivek ji, how to do that with our framework
iOS Carer Application |  | Responder | 1. Emergency/Non-Emergency alerts flow 2. Check schedule visit of carer and also details of task 3. Change temperature and mode of day/night 4. Check user status of service user, carer visit details, and sleep quality 5. Set schedule for heating, sleep schedule, Away settings, feedback 6.Send app logs | Pending | Currently our automation framework does not support IOS application automation
| Sankalp | carer | 1.Visit reminder messaged 2. Schedules | Pending | Currently our automation framework does not support IOS application automation
| Sankalp | Log out | Auto log from apps | Pending | Currently our automation framework does not support IOS application automation
Regression |  | Integration with all alerts | Integration with all alerts | In Progress | 1. Need to work on multiple device integration. -- Done 2. Manual command for allert generation. -- Done 3. Once the SOS cycle is completed other will be similar to work on. -- In porgress | 15 Days (3 Weeks)
Hurdle
Multiple device switching. Dependancy on vivek ji
Need canvas data for dashboard automation. Need R&D by Abhishek. Help required by Vivek ji
Need to do query execution for report and dashboard automation. Depandancy on Vivek Ji for how to do this in framework.
Need to work on alert generation through automation command like fall, temp, sleep etc for remaining regression cycle
Need to automate Gmail for logs sending automation. R&D required on Abhishek
Revise test case plan to cover every component of BB case project. Dependancy on Nirmal Ji.
Need to work on dataset for test cases which required updation before every regression cycle.
Commissioning and Decommissioning is not included in this automation cycle
Provided multiple devices solition drawback - Have to change control file, keyword sheet when we change the device.

## PUC
Software Installation |  | Software installation and code run on system |  | Done
SOS cycle from tablet and veriy at SP | Shyam | 1 | SOS Alert gnerated from tablet and closed from tablet | Done
| Shyam | 2 | SOS Alert Escalated to R1 and closed Verify on SP | Done
| Ankit | 3 | SOS Alert Escalated to R1 and accept and follow cycle and escalate to CRA and then closed Verify on SP | Done
|  | 4 | SOS Alert Escalated to R2 and closed Verify on SP | Done
| Shyam | 5 | SOS Alert Escalated to R2, Accept, Follow up cycle and escalated to CRA then closed Verify on SP | Done
| Shyam | 6 | SOS Alert Escalated to CRA and closed Verify on SP | Done
| Shyam | 7 | SOS Alert escalated to CRA without assigning responder and closed Verify on SP | Done
Multiple Interface ( Apps) switching - R&D |  | Switching between two android carer application with tablet app and SP for verify |  | Done
Fall alert cycle - R&D as dependency on sensors | Sachin | 1 | SOS Alert gnerated from tablet and closed from tablet | Done
| Jyoti | 2 | SOS Alert Escalated to R1 and closed Verify on SP | Done
|  | 3 | SOS Alert Escalated to R1 and accept and follow cycle and escalate to CRA and then closed Verify on SP | Done
| Sachin | 4 | SOS Alert Escalated to R2 and closed Verify on SP | Done
| Sachin | 5 | SOS Alert Escalated to R2, Accept, Follow up cycle and escalated to CRA then closed Verify on SP | Done
| Sachin | 6 | SOS Alert Escalated to CRA and closed Verify on SP | Done
| Sachin | 7 | SOS Alert escalated to CRA without assigning responder and closed Verify on SP | Done
Sachin
File insertion to portal with help of framework |  | Performing OTA, importing asste files of Gateway |  | Pending
Regression cycle - R&D |  | 1 | Sleep report in Carer App | Done
|  | 2 | User status in Carer App | Done
|  | 3 | AWAY settings | Done
|  | 4 | Sent logs | Pending
5
6
Merging of files | Sankalp | Merged files for testing
Git Commit | Sankalp | Git commit of files
Scheduler for Admin portal

## Consolidated plan
 | time axis 2024-08-01 to 2024-11-29
SN | Task detail | Detailed Task | Task dependency | Task dependency Id | Risk | Hurdle | Start date | Duration | Finish date | Actual Days | Status | Remarks | bar: 2024-08-08 to 2024-08-09; 2024-08-15 to 2024-08-16; 2024-08-22 to 2024-08-23; 2024-08-29 to 2024-08-30; 2024-09-05 to 2024-09-06; 2024-09-12 to 2024-09-13; 2024-09-19 to 2024-09-20; 2024-09-26 to 2024-09-27; 2024-10-03 to 2024-10-04; 2024-10-10 to 2024-10-11; 2024-10-17 to 2024-10-18; 2024-10-24 to 2024-10-25; 2024-10-31 to 2024-11-01; 2024-11-07 to 2024-11-08; 2024-11-14 to 2024-11-15; 2024-11-21 to 2024-11-22; 2024-11-28 to 2024-11-29
1 | Software installation and code run on system | Software installation and code run on system |  |  |  |  | 2024-08-01 | 2 | 2024-08-02 | 5 | Complete | Done | 2024-08-01: Sofware installation- Framework dependent software installation; 2024-08-02: Sofware installation- Framework dependent software installation; 2024-08-05: 1; 2024-08-06: 1; 2024-08-07: 0.5; 2024-08-10: 0.5; 2024-08-11: 0.5; 2024-08-12: 0.5; 2024-08-13: 0.5; 2024-08-14: 0.5
2 | SOS cycle from tablet and veriy at SP | [5 empty] | 2024-08-05 | 1 | 2024-09-10 | 1 | Complete | bar: 2024-08-07
| Fall alert cycle - dependency on sensors | [5 empty] | 2024-09-11 |  | 2024-09-18 |  | Complete
3 | Perform OTA with help of framework | [5 empty] | 2024-09-09 |  | 2024-09-12 |  | Pending | bar: 2024-08-10
4 | Support Portal/ Admin Portal - User form creation & deletion | [5 empty] | 2024-09-16 |  | 2024-10-04 |  | In Progress | Admin Portal: Entry Forms scripts are prepared. Working on remaining forms, reports. Support Portal is pending. | bar: 2024-08-11 to 2024-08-13
5 | Remaining Regression cycle | [5 empty] | 2024-10-07 |  | 2024-10-18 |  | In Progress | Working on Away and Sleep schedule
6 | iOS carer application | bar: 2024-08-19 to 2024-08-21; 2024-08-24 to 2024-08-28; 2024-08-31 to 2024-09-04; 2024-09-07 to 2024-09-08

## Daywise sheet
Function/Week | FPR | 2024-08-01 | 2024-08-02 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-17 | 2024-08-18 | 2024-08-19 | Remarks
Software Installation |  | Software installation and code run on system
SOS cycle from tablet and veriy at SP | Shyam | [17 empty] | Design (IRD,PRS,DES,RTM),GW registration,Sensor pairing, sensor removing,rule (Fall,sleep,QCA service), shedule
Shyam
Ankit
Shyam
| Shyam | [17 empty] | PR fixing, Decommission, Device monitor,system health,Led,button,SAST
Shyam
Ankit
Shyam
Shyam
Shyam
Shyam
Shyam
Andriod Tablet | Jyoti | Design interface
| Sachin |  |  |  | Development and Unit Testing
| Jyoti |  |  |  | Git and build activities
Integration testing
| Sachin | [7 empty] | Build1
| Sachin | [8 empty] | PR Fixing
| Sachin | [8 empty] | Develoment & unit testing
| Sachin | [11 empty] | SAST
Integration Testing
| Sachin | [12 empty] | Build2
Support Portal | Aman | Design
| Manvendra |  |  | Development & unit testing
| Aman | [5 empty] | GIT and Build
Integration testing
| Manvendra | [7 empty] | Integration testing |  |  |  |  | Agile activity
Hardware | [8 empty] | Build1
Mechanical | Sankalp | NPR & Printing Drawings Pilot Release
| Sankalp |  |  |  |  | Pre-Pilot trials for printing
| Sankalp | [12 empty] | Release of Double dash bom
| Sankalp | [15 empty] | Production Release of printing Files
Development (all functions) | All | [7 empty] | Integration testing |  |  |  | Integration testing
Validation | [9 empty] | Validation activity related to Gateway registration flow, sleep,fall,QCA and Schedule |  |  |  | PR Verification, Decommissioning flow, Sensor and Tablet unreachable, Skyline Led & push button functionality |  |  | Regression Suit ,DAST and Release Activity
Application Engineering | Mayank Vardia / Akash Agarwal | [13 empty] | Product configurator
|  | Critical |  | Pending | WIP | Done

## Scope1
Scope
SOS cycle from tablet and veriy at SP
Fall alert cycle - dependency on sensors
Perform OTA with help of framework
Support Portal/ Admin Portal - User form creation & deletion
Regression cycle
Not in scope
VoIP Call will not test
Email check for alerts and follow up
Challenges
Multiple apps handling and devices
Support portal runs on Firefox only - Compatibity code for firefox
Time gap between alert escalations
Differentiate between alerts on Support portal - Id or Date/time ?
Differentiate between alerts in reponder app
Appium allow session for 90 secs only - how to make session for longer duration
Opening alert from push notifications
iOS Support in framework
Merging of files
Git Commit
Risks
AL Testing Builds
Leaves
Dependency on vivek Sir for framework errors

## Status-10May23 (hidden)
KKM PIR | ETA expected by May end Rest done for Production launch without RoHS Supply chain process - TBD
ELA Binary | QR code modifications in progress, expected by May end Rest done for production launch Supply chain process - TBD
BBC Gateway | Need pilot as printing & packing changed (is it needed?) Need to release
Skyline 410 gateway | Linux release pending Pilot pending (Why?) Duplicate beacon issue (can go with it) As router internet issue (>20 min due to SIM IP issue) and service discovery issue
BBOS | CPK, Packing, Pilot pending Integration testing pending
Router (optional) | TP Link hang problem (M2M SIM) Can we go with Huwai (GPRS not M2M SIM) Also explore Jio fiber or Jio Fi
UPS | Ready
Pressure mat (Chair) | Ready
Pressure mat (Bed) | Ready
Tablet app | BLE PIR & Binary sensor add, diagnostic & remove flow
PHP portal - 25 man days Rest components - 2 months Full solution don't know but planned is 31-Jul (need to crush) PHP outsource

## HLS-Consolidated May-30-2023 (hidden)
SN | Task Id | Task detail | Detailed Task | Task dependency Id | Task dependency Id | Risk | Resources | Start date | Duration | Finish date | Actual Days | Last promis | Status | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04 | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02 | 2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-07-08 | 2023-07-09 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | 2023-07-16 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-22 | 2023-07-23 | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28 | 2023-07-29 | 2023-07-30 | 2023-07-31 | 2023-08-01
| HLS9 | Admin Portal Device Data Unit testing - check respected database entries to store history data and display at admin portal end for all type of sensors 2 days Display Device data at Admin portal for BBOS , KKM PIR, Ela DI sensors i.e. battery , weight, detection 2 days All sensor pairing with help of tablet 1 days To check that the data get insert in raw_log table and then display it at admin portal 2 days If fails find the cause , make required changes try to display data for BLE sensors 3 days. Unit testing - check data should get insert in respected DB and display it on admin portal for all type of sensor --2 days |  |  |  | Two different dll for BBOS & Other sensors from the firmware team for Skyline 410. F/W team took the previous gateway for issue resolution, Skyline gateway keeps changing. | Mayuri | 2023-05-17 | 12 | 2023-06-01 | 12 |  | In progress | [7 empty] | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1
| HLS8 | Admin Portal Sensor Entries in DB master tables To make Entry of Sensor details in zwave_node (Master Table) and Zwave_node_vlaue(feature of sensors) with searching the sensor related column Details |  |  |  |  | Mayuri | 2023-05-16 | 1 | 2023-05-16 | 2 |  | Done | [5 empty] | 1 | 1
| HLS7 | Database merging & testing On going activity Changes consolidation. - Sensor entries for BBOS, PIR, Binary -- Rule template changes . -- Function changes -- Table structural changes --Merging of 001 branch and skyline DB | Script creation, updation is part of individual activity |  |  |  | Aman | On going activity |  | 2023-07-06 | 0 | 2023-07-06 | Not started. | [7 empty] | .1 | .1 | .1 |  |  | .1 | .1 | .1 | .1 | .1 |  |  | .1 | .1 | .1 | .1 | .1 |  |  | .1 | .1 | .1 | .1 | .1 |  |  | .1 | .1 | .1 | .1 | .1 |  |  | .1 | .1 | .1 | .1 | .1 |  |  | .1 | .1 | .1 | .1 | .1 |  |  | .1 | .1 | .1 | .1
| HLS6 | Support portal --Screen changes TimeZone issue fixing Report changes [Optimistic time] a. Verify the reports for India Time zone - 2 days b. Changes required if any - 4 days |  |  |  |  | Aman | 2023-06-21 | 4 | 2023-06-26 | 3 |  | YTS | [35 empty] | 1 | 1 | 1
| HLS5 | Support portal -- Skyline Diagnostics a. Understanding and implementation - 2 days b. Code changes - 1 day c. Unit testing - 1 day |  | FW4 (18-06-2023) |  |  | Aman | 2023-06-15 | 4 | 2023-06-20 | 3 |  | YTS | [30 empty] | 1 |  |  | 1 | 1
| HLS4 | Support portal -- Reverse SSH a. Understanding Reverse SSH. 2 days B. Setting up changes on the server for India AL - 1 day c. code changes - 1 day d. Unit testing - 1 day |  | FW4 (18-06-2023) |  | SSH server creation might be required. | Aman | 2023-06-08 | 5 | 2023-06-14 | 5 |  | In progress | [26 empty] | 1 | 1 | 1 | 1 | 1
| HLS32 | iOS Compatibility | Version 16.x application crashing. VOIP socket causing the issue, third party liberary to be repalced as it is no longer supported |  |  |  | Yogyata | 2023-05-22 | 8 | 2023-06-01 |  |  | In progress
| HLS30 | Android integraton testing | Integration testing of Android tablet & Android mobile |  |  |  | Sachin Kumawat |  |  | 2023-07-10
| HLS3 | Support portal -- Skyline 410 OTA a. Understanding OTA - 2 days b. OTA repo creation - 1 day c. Settings change and code changes - 1 day d. Unit testing 1 day Note: Aman to work with Jitendra Pemawat to understand the flow |  | FW4 (18-06-2023) |  | OTA understanding may take time. | Aman | 2023-06-01 | 5 | 2023-06-07 | 5 | [21 empty] | 1 | 1 | 1 | 1 | 1
| HLS28 | UK flow verification on India AL merge code | Verify all the UK & India flow: 1.Create new installation using BBC gateway. 2. Pairing tablet. 3. Pairing Sensors. 4. CO alert validation. 5. Temprature alert validation. 6. Fall alert verification 7. SOS alert verification 8. Varification of data on tablet, Andorid mobile & iOS mobile 9. Admin portal verification of all the functionality. 10. Support portal varification of all the functionality. 11. Batch Processor verification of all the flows. |  |  |  | Aman & LST's |  |  | 2023-06-23
| HLS27 | Send log API development | Sending log from tablet using .NET core API Amit G. Commented this is not a mendatory for India AL and he will communicate to senior management [Meeting May-30-2023 10:30 am till 12:45 pm] | HLS22 |  |  | Manvendra Singh Rawal [LST] |  |  | 2023-06-16
| HLS26 | UAT server deployment |  | HLS25,VAL12 |  |  |  | 2023-07-17 | 2 | 2023-07-18 | 2 | [70 empty] | 1 | 1
| HLS25 | DCO activities 1. DB script consolidation with git commit and tag on git portal 2. Support portal code and configuration with git commit with git commit and tag on git portal 3. Admin portal code and configuration with git commit and tag on git portal 4. Batch Processor code and configuration with git commit and tag on git portal 5. iOS code and configuration with git commit and tag on git portal 6. Android tablet app code and configuration with git commit and tag on git portal & publish on Play store (?) | 1. DB script consolidation with git commit and tag on git portal 2. Support portal code and configuration with git commit with git commit and tag on git portal 3. Admin portal code and configuration with git commit and tag on git portal 4. Batch Processor code and configuration with git commit and tag on git portal 5. iOS code and configuration with git commit and tag on git portal 6. Android tablet app code and configuration with git commit and tag on git portal & publish on Play store (?) | HLS24 |  |  |  | 2023-06-26 | 9 | 2023-07-07 | 8 | [51 empty] | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
| HLS24 | System integration testing, reviews & feedback / bug fixing |  | FW25 |  |  |  | 2023-06-28 | 7 | 2023-07-06 | 7 | [51 empty] | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1
| HLS23 | Android Mobile Sign IN with India and UK User Sign in checked for India and Uk user differently working but testing with carer and secondary responder login pending |  |  |  |  | Jyoti |  | 2 |  | 0
| HLS22 | Android Tablet Flow test of Tablet app components 1.User Profile -- .5 day 2. Send Log -- 4 days 3. Installer menu all options -- 2 days 4. Fixed PR'S Testing and merge code testing which covers android compatibility -- 2 days 5. Compatible for INDIA and UK both flow testing -- 2 days 6. Unit testing flow --1.5 days 7. Integrated Testing -- 2 days |  | FW20(30-06-2023) |  | Send log api flow test with new integration .NET api and for large file has some risk. On large traffic network Reconfigure wifi and commissioning flow might get impact. Availability of sensors, gateway, tablet | Jyoti | 2023-06-21 | 14 | 2023-07-10 | 14 | [42 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1
| HLS21 | Android Tablet UI/Design Login Screen Need improvement for large email - day |  |  |  |  | Jyoti | 2023-06-20 | 1 | 2023-06-20 | 1 | [39 empty] | 1
| HLS20 | Android Tablet Remove device for Z-wave -- 2 days Adding Zwave Remove device Option in Menu requires design change and coding of remove device |  |  |  |  | Jyoti | 2023-06-16 | 2 | 2023-06-19 | 2 | [37 empty] | 1 | 1
| HLS2 | Batch processor code merging & testing a. Merging of 001 branch and skyline -4 days b. Testing the code - 2 days c. Bug fixing - 2 days | Alert flow design |  |  |  | Aman | 2023-05-19 | 8 | 2023-05-30 | 7 | 2023-06-05 | Issue with alarm generation time | [8 empty] | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
| HLS19 | Android Tablet Rules 1. BBOS 2. KKM PIR -- 2 days 3. ELA PIR and Binary (Fall and sleep rule, occupancy rule data and as per according to sensor) -- 3 days |  | HLS11(29-06-2023) |  | Which rule to display when there is BLE and Zwave device both | Jyoti | 2023-06-09 | 5 | 2023-06-15 | 5 | [30 empty] | 1 | 1 | 1 |  |  | 1 | 1
| HLS18 | Android Tablet Functions 1. BBOS (Weight and Battery status) 2. KKM PIR (State and Battery) 2 days 3. ELA PIR and Binary (State and battery and temperature) 2 days 4. Checking data in raw logger and api and functionlog table if it not displaying state 2 days | Design TBD |  |  | Availability of sensors, gateway | Jyoti | 2023-06-01 | 6 | 2023-06-08 | 5 | [23 empty] | 1 | 1 | 1 |  |  | 1 | 1
| HLS17 | Android Tablet KKM PIR Remove Device 1. Removing sensor from Tablet app 2. API 3. Removing from Portal |  | FW1,FW2 (28-05-2023) |  | Availability of sensors, gateway | Jyoti | 2023-05-30 | 2 | 2023-05-31 | 2 | [21 empty] | 1 | 1
| HLS16 | Android Tablet KKM PIR Update 1. Sensor location and area 1 day 2. Sensor data check at admin portal 1 day |  | FW1,FW2 (28-05-2023) |  | Two different dll for BBOS & Other sensors from the firmware team for Skyline 410. F/W team took the previous gateway for issue resolution, Skyline gateway keeps changing. | Jyoti | 2023-05-26 | 2 | 2023-05-29 | 2 |  | Work started | [15 empty] | 1 | 1
| HLS15 | Android Tablet KKM PIR Add 1. Sensor data in Gateway .5 day 2. Skyline DLL File and network problem .5 day 3. Sensor pairing data in Skyline .5 day 4. Sensor data into Raw logger 2 day 5. installation api for devices , function detail and master table entry" 2 days |  | FW1,FW2 (28-05-2023) |  | Skyline network is issue and blocker for application. With no internet functionality not work. | Jyoti | 2023-05-19 | 5 | 2023-05-25 | 4 |  | On track | [9 empty] | 1 |  |  | 1 | 1 | 1
| HLS14 | Android Tablet Commissioning Flow 5 days Switching between network get automatically connected issue in Android 10 Pending in Android 10, Working in android 11 |  |  |  | Network get automatically switching as Android os checking for best Wi-Fi range. For this have to forgot every time the previous network before switching to new | Jyoti | 2023-05-12 | 5 | 2023-05-18 | 5 |  | Done |  |  | 1 |  |  | 1 | 1 | 1 | 1
| HLS13 | Admin Portal Display History To check from where the history data get inserts in sqrawlog.dsp table and from this table data should get insert in function log Table -- 1 days If data gets store in respected tables then make it display at Admin portal end -- 1 days If Fails find the cause , make required changes try to display data -- 2 days Mayuri jointly investigated this issue with Amrit, and the changes were done on the Firmware end |  |  |  |  | Mayuri | 2023-07-04 | 4 | 2023-07-10 | 2 | [8 empty] | 1 | 1
| HLS12 | Admin Portal Zip code To understand the flow of execution for zip code adding address format -- 2 days To make the changes in Address table in DB if require 1 days To make the modification in code 2 days Unit testing - to create user with Indian zip code and to verify the value get save in DB 1 days Addresss length increased from current 100 character to 1000 characters |  |  |  |  | Tejasi | 2023-05-30 | 15 | 2023-06-19 | 15 | [22 empty] | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1
| HLS11 | Admin Portal Rules --16 days with Puneet support Understandings the concept of Rules and flow of execution in project with the help of Puneet ( Amrit sir if required ) -- 5 days Analize the changes required for BLE Sensors and modify the code as per requirement -- 3 days To make changes in template code required for different rules as per different sensors -- 4 days Provide the rule data for BLE sensors to Tablet end through APIs -- 2 days Unit testing - to check the rule data get display at admin portal end and passes same data to Tablet by testing API at postman tool -- 2 days |  | FW5,FW6 (25-06-2023) |  |  | Mayuri | 2023-06-08 | 16 | 2023-06-29 | 16 | [31 empty] | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1
| HLS10 | Admin Portal API Sensor Pairing the Tablet and display data at both end Pair total 4 BBOS sensors , display battery and weight data at both Admin and tablet end 1 day Pair 2 KKM PIR sensor , display battery and detection at both Admin and tablet end thought API 1 day Pair 2 Ela DI sensor , display battery and detection at both Admin and tablet end thought API 1 day |  | FW1,FW2 (28-05-2023) |  | Two different dll for BBOS & Other sensors from the firmware team for Skyline 410 | Mayuri | 2023-06-02 | 4 | 2023-06-07 | 4 | [25 empty] | 1 |  |  | 1 | 1 | 1
| HLS1 | Support portal code merging & testing a. Merging of 001 branch and skyline. - 3 days b. Testing the code - 2 days c. Bug fixing - 2 days |  |  |  |  | Aman | 2023-05-10 | 7 | 2023-05-18 | 6 |  | Complete | 1 | 1 | 1 |  |  | 1 | 1 | 1
| HLS | UAT environment recovery | Issue identified, script provided to Liberty help desk for daily monitoring |  |  |  | Nishchal |  |  | 2023-05-15 |  |  | Complete
| HLS | Score card data issue --Lisa | Discussion done, data already in place. Explained that there is no impact on the restoredby column post Mole Valley Phase-II |  |  |  | Nishchal | 1900-05-23 | 0.25 | 2023-05-23 | 0.25 |  | Complete
| HLS | Planned Maintenance, Saturday, 27th May 2023 | Nishchal - Worked on staturday Discussion to shorten the down time to bare minimum. Preparation for maintenance - Anjali have now both the instance of Batch Processor running on her login so that she can independently stop and start the Batch processor on the planned maintenance day |  |  |  | Nishchal | 2023-05-23 |  | 2023-05-25 |  |  | Complete
| HLS | Support for PHP to .NET 6 migration & Traffic signal development: | 1. Dinesh Rathor -- Traffic signal development 2. Teh D. -- Resolving their queries and providing sample code and other support |  |  | Access to Development environment is restricted, development team member need to provide support on going basis for Traffic signal development | Nishchal | [5 empty] | On going activity
| HLS33 | BatchProcessor Time stamp | Email generation time stamp, time stamp in email and other time stamp issue reported by PV team |  |  |  | Aman

## Status
TC01 | Web | Get Current Alert ID | Done
| Android | Resolve SOS from Tablet | Done
| Web | Reverify Alert ID | Done
TC02 | Web | Get Current Alert ID | Pending | 1 | Three folder structure | Possible | 1-2 days
| Android | Generate SOS from Tablet | Done | 2 | Need to close alert through support portal.
| Android | Resolve From PR Mobile | Done | 2 | Intergation between test case | Need R&D | 3-5 days
| Web | Reverify Alert ID | Pending | 3 | Verification of each test case | Possible but need time | 2-3 days
TC03 | Web | Get Current Alert ID | Pending
| Android | Generate SOS from Tablet | Done
| Android | Accept and Check follow up msg on PR Mobile | Done
| Web | Close the Panic from CRA | Pending
TC04 | Web | Get Current Alert ID | Pending
| Android | Generate SOS from Tablet | Done
| Android | Reject From PR | Done
| Android | Accept and Close the Panic from SR | Done
| Web | Reverify Alert ID | Pending
TC05 | Web | Get Current Alert ID | Pending
| Android | Generate SOS from Tablet | Done
| Android | Reject From PR | Done
| Android | SR accept and check the follow up msg | Done
| Web | Close the Panic from CRA | Pending
| Web | Reverify Alert ID | Pending
TC06 | Web | Get Current Alert ID | Pending
| Android | Generate SOS from Tablet | Done
| Android | Reject from PR | Done
| Android | Reject from SR. | Done
| Web | Close the Panic from CRA | Pending
| Web | Reverify Alert ID | Pending
TC07 | Web | Get Current Alert ID | Pending
| Web | Remove the PR and SR from Admin Portal | Done
| Android | Generate SOS from Tablet | Done
| Web | Close the Panic from CRA | Pending
| Web | Reverify Alert ID | Pending
| Web | Add the PR and SR from Admin Portal | Done

## Sheet1
S.No. | Tool | Total Test Cases | Total Automation Test Planned | Test Automation Completed | Pending | Automation Not Doing | Remarks | Status
1 | Regression Cycle | 27 | 18 | 18 | 0 | 9 |  | Under Progess
2 | Admin Portal
3 | Support Portal
4 | CareFor App
5 | Carer App